## Risk Register
NRW Logistics GmbH — ISMS Risk Register
ISO/IEC 27001:2022 Clause 6.1.2 — Quantitative risk assessment (SLE x ARO methodology). See 'Methodology & Notes' tab.
Risk ID | Asset / Process | Threat | Vulnerability | Existing Controls | Asset Value AV (EUR) | Exposure Factor EF (%) | SLE (EUR) | ARO (per year) | ALE (EUR) | Inherent Risk Rating | Risk Treatment Decision | Treatment / Recommended Control | Residual EF (%) | Residual SLE (EUR) | Residual ARO | Residual ALE (EUR) | Residual Risk Rating | Risk Owner | Status | Review Date
R-001 | HQ network — email | Phishing leading to credential compromise | No email filtering beyond default spam rules; users not trained on phishing recognition | Basic spam filter only | 40000 | 50% | 20000 | 3 | 60000 | Critical | Mitigate | Deploy advanced email filtering (attachment/URL sandboxing); run quarterly phishing simulation and awareness training | 20% | 8000 | 1 | 8000 | Medium | IT Manager | Open | 2026-11-01
R-002 | Warehouse WMS | Ransomware infection on WMS server | WMS server not network-segmented from general office LAN; irregular patching cadence | Nightly backups (untested restore) | 120000 | 70% | 84000 | 0.5 | 42000 | High | Mitigate | Segment WMS on isolated VLAN; enforce monthly patch cycle; test backup restoration quarterly | 30% | 36000 | 0.2 | 7200 | Medium | Warehouse Ops Lead | Open | 2026-10-15
R-003 | Fleet telematics | Remote exploitation of unpatched telematics platform | Vendor firmware updates applied irregularly; platform exposed to internet for remote tracking | Vendor-managed authentication only | 60000 | 50% | 30000 | 1 | 30000 | High | Mitigate | Enforce vendor SLA for patch timelines; restrict platform access via IP allow-listing and VPN | 25% | 15000 | 0.5 | 7500 | Medium | Fleet Operations Manager | Open | 2026-11-15
R-004 | Cloud ERP (Azure) | Misconfigured access controls exposing financial/customer data | Shared admin accounts; no periodic access review | Azure default RBAC (not reviewed) | 90000 | 60% | 54000 | 1 | 54000 | Critical | Mitigate | Implement least-privilege RBAC; enforce MFA on all admin accounts; quarterly access recertification | 20% | 18000 | 0.3 | 5400 | Medium | IT Manager | Open | 2026-10-01
R-005 | End-user devices | Loss or theft of laptop containing customer shipment data | No full-disk encryption enforced; no remote wipe capability | Password login only | 15000 | 80% | 12000 | 2 | 24000 | High | Mitigate | Enforce BitLocker full-disk encryption fleet-wide; enable MDM remote wipe | 10% | 1500 | 2 | 3000 | Low | IT Manager | Open | 2026-09-30
R-006 | Warehouse WMS | Insider misuse of WMS access to divert or falsify shipments | No segregation of duties between order entry and dispatch approval | Manual supervisor spot-checks | 50000 | 40% | 20000 | 0.5 | 10000 | Medium | Mitigate | Implement segregation of duties in WMS workflow; enable audit logging with monthly review | 20% | 10000 | 0.3 | 3000 | Low | Warehouse Ops Lead | Open | 2026-12-01
R-007 | Cloud ERP (Azure) | DDoS attack disrupting order processing availability | No DDoS protection tier enabled on Azure resources | Default Azure network security groups | 70000 | 30% | 21000 | 0.5 | 10500 | Medium | Transfer | Enable Azure DDoS Protection Standard (shifts residual risk to cloud provider's mitigation SLA) | 15% | 10500 | 0.3 | 3150 | Low | IT Manager | Open | 2026-11-01
R-008 | Customs broker API interface | Compromise of third-party API leading to shipment data leakage | API keys not rotated; no request rate limiting | TLS in transit only | 35000 | 60% | 21000 | 1 | 21000 | High | Mitigate | Rotate API keys quarterly; implement rate limiting and request logging on the interface | 25% | 8750 | 0.5 | 4375 | Low | IT Manager | Open | 2026-12-15
R-009 | Backup infrastructure | Backup failure or corruption after a ransomware event | Backups stored on same network segment as production; restores untested | Nightly automated backup job | 120000 | 50% | 60000 | 0.5 | 30000 | High | Mitigate | Implement offline/immutable backup copy (3-2-1 strategy); quarterly restore testing | 15% | 18000 | 0.2 | 3600 | Low | IT Manager | Open | 2026-10-30
R-010 | HQ network — admin accounts | Brute-force compromise of admin accounts due to weak password policy | Minimum 8-character password policy; no account lockout threshold | Basic Active Directory password policy | 45000 | 50% | 22500 | 1.5 | 33750 | High | Mitigate | Enforce 14-character minimum with complexity; enable account lockout after 5 attempts; deploy MFA | 15% | 6750 | 0.3 | 2025 | Low | IT Manager | Open | 2026-09-15
R-011 | Remote access VPN | Unauthorized remote access due to lack of MFA on VPN | Single-factor VPN authentication (password only) | VPN with password authentication | 55000 | 50% | 27500 | 1 | 27500 | High | Mitigate | Enforce MFA on all VPN connections; review VPN access logs monthly | 15% | 8250 | 0.3 | 2475 | Low | IT Manager | Open | 2026-09-01
R-012 | Fleet telematics | GPS spoofing or tampering affecting delivery route integrity | No anomaly detection on route deviation; sensor data not cross-validated | Manual dispatcher review of routes | 25000 | 40% | 10000 | 0.5 | 5000 | Medium | Accept | Risk accepted at current exposure; monitor vendor roadmap for anomaly detection features | 40% | 10000 | 0.5 | 5000 | Medium | Fleet Operations Manager | Open | 2027-03-01
Note on F4: Asset Value: the estimated financial value of the asset if lost, including replacement cost and business impact.
Note on G4: Exposure Factor: the percentage of asset value that would realistically be lost in a single incident, not always 100%.
Note on H4: Single Loss Expectancy = Asset Value x Exposure Factor. The expected cost of ONE occurrence.
Note on I4: Annualized Rate of Occurrence: how many times per year this risk is expected to materialize, based on threat intelligence, incident history, or industry benchmarks.
Note on J4: Annualized Loss Expectancy = SLE x ARO. The expected yearly financial impact — this is what risk appetite and budget decisions should be based on, not the raw SLE.

## Methodology & Notes
Risk Assessment Methodology — GRC Analyst Notes
Why quantitative risk assessment (SLE x ARO), not just High/Medium/Low
A purely qualitative 'High/Medium/Low' rating is fast but hard to defend to management — it doesn't translate to budget decisions. SLE x ARO gives every risk a defensible annual euro figure (ALE), so treatment decisions can be compared against control cost directly: if a control costs more per year than the ALE it reduces, it's hard to justify. This is the same logic examiners and auditors expect to see behind a risk register, not just color-coded guesses.
SLE = Asset Value x Exposure Factor
Single Loss Expectancy is the expected cost of ONE occurrence of the risk. Asset Value should reflect realistic financial and reputational impact, not just hardware replacement cost — for example, WMS downtime costs more in lost fulfillment revenue than the server itself is worth. Exposure Factor is rarely 100%: a ransomware event on a segmented, well-backed-up system might only realistically destroy 30-50% of value, because recovery is possible.
ALE = SLE x ARO — this is the number that matters
Annualized Loss Expectancy converts a one-time loss into an annual figure by factoring in how often the event is expected. A catastrophic event that happens once every 20 years (ARO = 0.05) may have a lower ALE than a frequent, low-impact event — and therefore a lower budget priority, even though it 'feels' scarier. This is why ALE, not SLE alone, should drive treatment prioritization and risk appetite discussions.
Risk rating thresholds used in this register
Low: ALE under €5,000 — typically accepted or handled through routine operational controls. Medium: ALE €5,000-€19,999 — mitigated within normal budget cycles. High: ALE €20,000-€49,999 — requires documented treatment plan and management visibility. Critical: ALE €50,000+ — requires immediate treatment and senior management/board attention. These thresholds are illustrative for this portfolio project — in practice they should be set by management based on the organization's actual risk appetite.
The four risk treatment options (ISO/IEC 27001:2022 Clause 6.1.3)
Mitigate: reduce likelihood or impact by implementing a control (the most common treatment — most rows in this register). Transfer: shift financial impact to a third party, e.g. cyber insurance or a cloud provider's SLA (see R-007, DDoS protection). Accept: consciously accept the risk when treatment cost exceeds benefit, always with documented justification and an owner (see R-012). Avoid: eliminate the risk entirely by discontinuing the activity that causes it — not used in this register, but relevant when a legacy system or process carries risk disproportionate to its business value.
Why residual risk matters as much as inherent risk
Inherent risk (columns F-K) shows exposure before any new controls are applied. Residual risk (columns N-R) shows exposure AFTER the recommended control is implemented. An auditor — or an interviewer — will specifically ask whether residual risk was calculated and whether it was reduced to an acceptable level, not just whether a control was recommended. A register that only shows inherent risk is incomplete.
Where this feeds into Phase 3 (Statement of Applicability)
Every 'Mitigate' treatment above should map to one or more Annex A controls in the SoA — the SoA's justification column should reference the specific risk ID it addresses (e.g. 'Applicable — mitigates R-004, R-010, R-011'). This traceability from risk to control is exactly what auditors check first, and it's the single clearest way to demonstrate risk-based thinking rather than template-copying in an interview.